## sprint backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | 1 | Collected Aadhaar and other KYC document images and prepared datasets for OCR, CNN, and ML models. Performed image preprocessing, normalization, QR extraction readiness, and metadata preparation for downstream validation. | 2025-12-05 | 2025-12-10 | piyush,roohi,shravani,aishwarya,vaishnavi,pakhee, | finding dataset | done | 12 hrs | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2; Day 6: 2
SPRINT 2
2 | 2 | Implemented PaddleOCR to extract structured text fields from Aadhaar documents and generated standardized JSON outputs. Built OCR post-processing logic to clean text, validate formats, and prepare extracted data for rule-based and ML validation. | 2025-12-11 | 2025-12-15 | shravani | finding appropriate technique to extract data from image | done | 10hrs | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2
SPRINT 3
3 | 3 | Extracted Aadhaar QR code data and compared it against OCR-extracted fields using rule-based validation. Generated consistency scores and flags to detect mismatches between QR data, OCR text, and document structure. | 2025-12-15 | 2025-12-17 | Pakhee,Aishwarya,roohi | rule based validation to compare Aadhar QR data and OCR extracted fields | done | 7hrs | Day 1: 2; Day 2: 3; Day 3: 2
SPRINT 4
4 | 4 | Developed a CNN model to classify documents as real Aadhaar, fake Aadhaar, or non-Aadhaar images. Integrated image forensics features to detect tampering indicators such as overlays, font inconsistencies, and artifacts. | 2025-12-15 | 2025-12-16 | Piyush | I used a transfer learning to predict fake aadhaar, non_Aadhaar, fake_Aadhaar | done | 5hrs | Day 1: 2.5; Day 2: 2.5
SPRINT 5
5 | 5 | Performed face extraction from Aadhaar photo and live/person image for comparison. Applied face-matching logic to verify identity consistency when the document is classified as a real Aadhaar. | 2025-12-27 | 2025-12-27 | SHRAVANI | I used a pretrained model to extract a face from two image and outputed whether both image match | done | 3
SPRINT 6
6 | 6 | Designed an ML model that takes OCR data, QR validation results, and image forensics inputs. The model produces a final Real/Fake classification with confidence-based fraud risk assessment. | 2025-12-17 | 2025-12-18 | Ashish | I used the Random forest classification model which is trained on the output of ocr which is in json format and these json files data is extracted into the csv file and then the model got trainied on the dataset with the f1 score 0.9 | done | 12 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2; Day 6: 2
SPRINT 7
7 | 7 | Integrated OCR, CNN, QR validation, face matching, and ML models into a single end-to-end pipeline. Ensured smooth data flow between modules and real-time decision output in JSON format. | 2026-01-01 | 2026-01-02 | Piyush | manage in correct flow during to integration | done | 8hrs | Day 1: 4; Day 2: 4
SPRINT 8
8 | 8 | Tested the complete pipeline with multiple Aadhaar scenarios including genuine, tampered, and fake samples. Validated system accuracy, reduced false positives, and ensured readiness for cloud-based deployment. and ui part made | 2025-12-27 | 2026-01-03 | Aishwarya | Tested API ,working flow and Frontend part | done | 25hrs | Day 1: 4; Day 2: 5; Day 3: 4; Day 4: 3; Day 5: 3; Day 6: 3; Day 7: 2; Day 8: 2
Note on D1: ====== ID#AAABySIrxJc Please enter the dates in either of these formats (2026-01-06 15:39:39) 9/15/2016 or 15-Sep-2016
Note on E1: ====== ID#AAABySIrxIw Please enter the dates in either of these formats (2026-01-06 15:39:39) 9/15/2016 or 15-Sep-2016
Note on I2: ====== ID#AAABySdK7Mk Sumeet Kumar Barua08 (2026-01-06 15:39:39) This is the total task estimated in hours for all the user stories
Note on J2: ====== ID#AAABySIrxJY Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 1 work
Note on K2: ====== ID#AAABySIrxI4 Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 2 work
Note on L2: ====== ID#AAABySIrxJA Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 3 work
Note on M2: ====== ID#AAABySIrxIo Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 4 work
Note on N2: ====== ID#AAABySIrxJQ Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 5 work
Note on O2: ====== ID#AAABySIrxJM Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 6 work
Note on P2: ====== ID#AAABySIrxIs Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 7 work
Note on Q2: ====== ID#AAABySIrxI0 Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 8 work
Note on R2: ====== ID#AAABySdK7Mg Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 9 work
Note on S2: ====== ID#AAABySIrxIk Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 10 work
Note on T2: ====== ID#AAABySIrxJE Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 11 work
Note on U2: ====== ID#AAABySIrxI8 Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 12 work
Note on V2: ====== ID#AAABySIrxJI Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 13 work
Note on W2: ====== ID#AAABySIrxJU Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 14 work

## standup meetings
Sprint | Day | Impediments | Action Taken
1 | 2025-12-09 | unable to get fake data | we generated fake data
2 | 2025-12-14 | difficulty to get good ocr extraction | we used paddle ocr which gave far better results
3
4
5
6
7
8

## retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-12-05 | 2025-12-10 | piyush,shravani,aishwarya,vaishnavi,pakhee, | we started with kaggle and google search
2 | 2 | 2025-12-11 | 2025-12-15 | shravani
3 | 3
4 | 4
5 | 5 | 2025-12-27 | 2025-12-27 | SHRAVANI
6 | 6
7 | 7
8 | 8

## product backlog
Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 |  | Collected Aadhaar and other KYC document images and prepared datasets for OCR, CNN, and ML models. Performed image preprocessing, normalization, QR extraction readiness, and metadata preparation for downstream validation. |  | used google, kaggle,fake images generated for dataset, and preprocessing done using python libraries | everyone
2 |  | Implemented PaddleOCR to extract structured text fields from Aadhaar documents and generated standardized JSON outputs. Built OCR post-processing logic to clean text, validate formats, and prepare extracted data for rule-based and ML validation. |  | according to goverment rules validation done and ocr extraction techinques used | shravani
3 |  | Extracted Aadhaar QR code data and compared it against OCR-extracted fields using rule-based validation. Generated consistency scores and flags to detect mismatches between QR data, OCR text, and document structure. |  | qr decoder used | aishwarya
4 |  | Developed a CNN model to classify documents as real Aadhaar, fake Aadhaar, or non-Aadhaar images. Integrated image forensics features to detect tampering indicators such as overlays, font inconsistencies, and artifacts. |  | predefined cnn model used | piyush
5 |  | Performed face extraction from Aadhaar photo and live/person image for comparison. Applied face-matching logic to verify identity consistency when the document is classified as a real Aadhaar. |  | predefined model used | shravani
6 |  | Designed an ML model that takes OCR data, QR validation results, and image forensics inputs. The model produces a final Real/Fake classification with confidence-based fraud risk assessment. |  | coustmize model made | ashish
7 |  | Integrated OCR, CNN, QR validation, face matching, and ML models into a single end-to-end pipeline. Ensured smooth data flow between modules and real-time decision output in JSON format. |  | all parts were integrated | piyush
8 |  | Tested the complete pipeline with multiple Aadhaar scenarios including genuine, tampered, and fake samples. Validated system accuracy, reduced false positives, and ensured readiness for cloud-based deployment. and ui part made |  | Postman for API testing, HTML, CSS, JS for Frontend | aishwarya,vaishanavi
Note on E1: ====== ID#AAABySIrxIg Sumeet Kumar Barua08 (2026-01-06 15:39:39) Mention the US ID(s) on which the user story depends.